## The Cost Table
The Cost Table
Activity($) | Actual Cost ($) | Estimated Cost for Remaining Activities ($)
Prototypes | 25000 | 28000
Serial I/O drivers | 30000 | 24500
System hardware/software | 50000 | 34000
Order circuit boards | 8000 | 4000
Project documentation | 40000 | 27800
Network interface | 70000 | 65000
Shell | 60000 | 54800
Assemble preproduction | 15000 | 12000
Integrated acceptance | 90000 | 78000
Total Actual Cost | 388000 | 328100
Total Estimated Cost
Estimated at Completion (EAC) = Total Actual Cost + Total Estimated Cost = 388,000.00 + 328100.00 = $716100.00

## The Gantt Chart
Management:Gantt Chart
Activity Number | Description | Duration | Start Date | End Date | 2011-03-08 | 2011-06-30 | 2011-07-01 | 2011-07-25 | 2011-08-08 | 2011-08-12 | 2011-09-30 | 2011-10-01 | 10/14/11 | 2011-11-01 | 2011-11-15 | 2011-12-29 | 2012-02-20
1 | Prototypes | - | 2011-03-08 | 2011-03-08
2 | Serial I/O drivers | - | 2011-06-30 | 2011-06-30
3 | System hardware/software | 25 | 2011-07-01 | 2011-07-25
4 | Order circuit boards | 5 | 2011-08-08 | 2011-08-12
5 | Project documentation | 55 | 2011-08-08 | 2011-10-01
6 | Network interface | 99 | 2011-08-08 | 2011-11-15
7 | Shell | 55 | 2011-08-08 | 2011-09-30
8 | Assemble preproduction | 18 | 10/14/11 | 2011-11-01
9 | Integrated acceptance | 54 | 2011-12-29 | 2012-02-20